## Slide 1
PowerPoint Title 1
ccNSO Session Proposal: ZA Schools 9

## Slide 2
ZADNA on a Page
01
PRT1
PRT2
PRT3
PRT4
Comply with international best practice in the administration of the .ZA domain name space; license and regulate registries and registrars and publish guidelines on .ZA domain namespace.
The Authority must enhance public awareness on the economic and commercial benefits of domain name registration.
ZADNA is the custodian of the Internet Governance in South Africa.
The .za Domain Name Authority (ZADNA) is the statutory regulator and manager of ZA Namespace.

## Slide 3
Legislated Mandate
02
    ZADNA is a statutory, not-for-profit entity established in terms of Chapter X of the ECT Act 25 of 2002 to administer, manage and regulate the .ZA namespace. The mandate can be summed up as follows:
      The management and administration of the .ZA namespace;
      . ZA policy, licensing, and regulation;
      Monitoring and compliance;
      Domain name awareness and education;
      Research and development; and
      Making relevant policy recommendations to the Minister.
      Alternate Dispute Resolution Regulations
    Additional non-ECT Act Responsibilities
      dotCities
      Internet Governance

## Slide 4: BACKGROUND & OBJECTIVE OF INITIATIVE
ZA Schools Digitisation Project

## Slide 5
Problem Statement
03
Goal 4 of the SDG: Ensure inclusive & equitable quality education & promote lifelong learning opportunities for all
The South African Constitution guarantees the right to basic education, including access to digital resources
The digital gap persists as a significant challenge, especially for schools in rural and disadvantaged areas
Despite policies and initiatives like SA Connect & USAOs, state efforts for digital infrastructure provision to schools have been disjointed & insufficient

## Slide 6
Problem Solution
04
01
02
03
04
05
06
Deploying 22 982 school.za domain names in three (3) years
Develop & deploy websites for all the beneficiary public schools
Provide emails for 12 543 496 Learners & 402 961 Educators
Provide educators, parents, and learners with digital skills
Provide training opportunities unemployed youth nationwide
Provide ICT internship or leadership program to 250 to 500 unemployed youth nationwide

## Slide 7: PROGRESS…
ZA Schools Digitisation Project

## Slide 8
Administrative millstones
05
Department of Communication and Digital Technologies endorsed the project
ZADNA is the project custodian with implementation from relevant stakeholders
Memorandum of Understanding (MoU) with USAASA for funding
  Initial funding of 11 million rand secured
Google collaboration for learning classrooms and platforms
MoUs with Free State and Northern Cape Department of Education for project endorsement.
Partnership with National Electronic Media Institute of South Africa (NEMISA) for Digital Literacy Cybersecurity and safety training targeted at: Educators, Learners, and Parents.

## Slide 9
Technical Millstones
06
Deployed 6.4% school.za domain names in 6 months. 22% school.za domain names scheduled for the 2024/25 FY
01
Provided emails for 10.2% Learners & 10.2% Educators
03
Provide training opportunities 0% unemployed youth nationwide
all
05
Developed & deployed 3 websites for 3 public schools
02
6.4% educators, parents, and learners provided with digital skills
04

## Slide 10: ANALYSIS OF PROGRESS…
ZA Schools Digitisation Project
Progress lies not in enhancing what is, but in advancing toward what will be. - Khalil Gibran

## Slide 11
Initiative Challenges
07
Description | Challenge | Impact
Resource Allocation | Limited resources such as funding and manpower hinder the smooth execution of the project. | 3.9% of funding has restricted the scope and reach of the project, while 0.1% manpower has resulted in delays in project implementation.
Technical Complexity | Connectivity issues, especially in remote underprivileged areas. | Connectivity issues impedes the successful implementation of the project by disrupting communication and hindering the effective integration of technology into the learning platform.
Capacity Building | Delays in building the capacity of educators, students, and support staff to effectively utilize digital platforms. | Educators, students, and support staff are hesitant to embrace the learning platforms, resulting in a slow adoption rate and reluctance to explore other innovative feature for teaching.
Stakeholder Engagement | Limited buy-in from enablers of deployment such as Provincial Departments of Education and local communities, to address unique needs and concerns regarding education. | Though we have full buy-in from Provincial governments in the Free State and Northern Cape, other provincial governments are not a forthcoming, presenting a a challenge of collaboration, which undermines the sustainability of the project.

## Slide 12
Initiative Success Factors
08

## Slide 13
Measure outcome matrix
09
Infrastructure & Technology Deployment
Usage of digital learning resources and platforms.
Teacher and Student Engagement
Frequency of teachers using learning platform and integrating it into teaching practices.
Stakeholder Satisfaction
Student and teacher satisfaction, colupled with parental involvement and undrstanding of learning platform
Operational Efficiency
Improvements in school administration and management through learning platform .

## Slide 14
Conclusion
10
Thanks!
Do you have any questions?
Tsholofelo@zadna.org.za
+27 10 020 3919
https://www.zadna.org.za

## Slide 15
Thank you – Questions and Discussion